## Sheet1
COSC1076 ¦ Semester 1 2024 |  |  | Bunchango/Fred-s-Tasty-Treat: Advanced Programming Technique's Assignment 2 (github.com)
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | Thu430-Group 4
Group Member: | Dong Manh Duc |  | Progress Classes: | Ahead
Group Member: | Nguyen Ba Duc Manh |  |  | On-track
Group Member: | Tran Tuan Trung |  |  | Behind
Way Behind
Tutor: | Paul Miller
Class: | Thu430
|  | Week 7 | Goals | Tutor Notes | Individual Updates | Dong Manh Duc | Nguyen Ba Duc Manh | Tran Tuan Trung | D
|  |  | Group Formed |  | Weekly Contribution | Created MS Team and Github Repo and invited members and uploaded startup code
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Individual Updates | Dong Manh Duc | Nguyen Ba Duc Manh | Tran Tuan Trung | D
|  |  | Choice of where to use linked list, vector & array, etc |  | Weekly Contribution
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues
|  |  | Main menu |  | Other Notes |  | Implemented Main menu
|  |  | User Prompt (for program), but no/minimal error checking |  |  |  |  | Add user prompt
|  |  | Linked List implementation |  |  | Add utility functions |  | Implemented basic of LinkedList
|  |  | Implementation(s) or suitable ADTs including expected behaviours |  |  |  | Planned ADTs
|  |  | ADT implementation for storing information |  |  |  | Implemented class to store data
|  |  | Handling coins and stock data files. |  |  | Implemented read file '
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Individual Updates | A | B | C | D
|  |  | Load/Save to/from data files (doesn't require integration with main menu) |  | Weekly Contribution | Implemented file reading |  | Implement file saving
|  |  | Display an item |  | Issues |  | Implemented dynamic display
|  |  | Purchcase an item |  | Other Notes |  |  | Implemented function for interface
|  |  | Insert and remove an item on the linked list |  |  | Implemented inserting | Implement removing item
|  |  | Write Tests Cases for common uses |  | Wrote quick tests
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Individual Updates | A | B | C | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Implement validation |  | Implement validation methods
|  |  | Full error checking of user prompt |  | Issues |  | Implement EOF checking
Other Notes
|  |  | Final Tests |  |  |  | Wrote final tests and check valgrind
|  |  | Group Report Written |  |  |  | Wrote report
|  | Progress | On-track